## Requirements
breachsafe-oscal - Requirements (RTM)
ID | Category | Requirement | Type | Priority | Grounding / Source | Acceptance Criteria | Verify | Status
ARCH: | Architecture | N sources -> neutral IR -> M targets
R-ARCH-01 | Architecture | Sources and targets are decoupled through a neutral intermediate representation (IR). | Constraint | Must | N->IR->M design | New source needs no emitter change and vice-versa. | Inspection | Designed
R-ARCH-02 | Architecture | Adding a source = one new adapter registered in a single place. | Functional | Must | cli._ADAPTERS registry | Register in _ADAPTERS only; emitters untouched. | Inspection | Designed
R-ARCH-03 | Architecture | Adding a target = one new emitter; adapters untouched. | Functional | Must | emitters/ package | New emitter consumes IR only. | Inspection | Designed
R-ARCH-04 | Architecture | IR is frozen, source/target-agnostic (Finding/Subject/Evidence/Risk). | Constraint | Must | ir.py frozen dataclasses | Dataclasses frozen; no source field names leak past adapter. | Inspection | Built
SRC: | Sources | Input adapters
R-SRC-01 | Sources | QuReddy qureddy.scan.v1 JSON adapter. | Functional | Must | adapters/qureddy.py | Live example.com scan -> IR findings + subject. | Demo | Built
R-SRC-02 | Sources | Prowler adapter. | Functional | Should | roadmap | Prowler OCSF/native output -> IR. | Test | Backlog
R-SRC-03 | Sources | OCSF adapter. | Functional | Could | roadmap | OCSF finding -> IR. | Test | Backlog
R-SRC-04 | Sources | CycloneDX CBOM adapter. | Functional | Could | roadmap; qureddy CBOM | CBOM crypto-assets -> IR. | Test | Backlog
R-SRC-05 | Sources | OpenTelemetry adapter. | Functional | Won't | roadmap | Deferred beyond this release. | - | Deferred
R-SRC-06 | Sources | Adapter fails loudly on unknown/unsupported schema version. | Non-functional | Should | - | Unsupported version raises, never silently maps. | Test | Open
OUT: | Targets | Output emitters
R-OUT-01 | Targets | OSCAL POA&M emitter (first target). | Functional | Must | emitters/poam.py | Emits plan-of-action-and-milestones with all required fields. | Demo | Built
R-OUT-02 | Targets | Output is standalone + human-readable (no base64, no mandatory external fetch). | Constraint | Must | Option A decision | Reader understands posture from the doc alone. | Inspection | Met (v2)
R-OUT-03 | Targets | Crypto facts carried as readable namespaced props (ns=https://breachsafe.ai/ns/oscal). | Functional | Must | v2 observation props | readiness/algorithm/level/cert-sig/hashes present as props. | Inspection | Met (v2)
R-OUT-04 | Targets | Optional CBOM companion via relevant-evidence href; POA&M valid without it. | Functional | Should | v2 relevant-evidence | Remove the link -> still validates. | Demo | Met (v2)
R-OUT-05 | Targets | Provenance in metadata (generator + responsible-party). | Functional | Should | v2 metadata | generator/version props + Prepared By party present. | Inspection | Met (v2)
OSC: | OSCAL Conformance | Schema + version
R-OSC-01 | OSCAL | Declared oscal-version = 1.1.2 for max validator interop; 1.2.2 recorded as internal target prop. | Constraint | Must | oscal-cli 3.2.0; Trestle regex ^1.2.[0-1]$ | Declared 1.1.2; prop oscal-target-version=1.2.2. | Inspection | Met (v2)
R-OSC-02 | OSCAL | All required POA&M fields present (uuid, metadata{title,last-modified,version,oscal-version}, system-id¦import-ssp, >=1 poam-item{title,description}). | Constraint | Must | oscal_poam_metaschema.xml | Validator reports required fields satisfied. | Demo | Met (v2)
R-OSC-03 | OSCAL | Output validates clean against NIST oscal-cli. | Non-functional | Must | ghcr.io oscal-cli:latest (3.2.0) | 'The file is valid.' exit clean. | Demo | PASS (v2)
R-OSC-04 | OSCAL | Element ordering conforms to the metaschema. | Constraint | Must | metaschema | No ordering errors from validator. | Demo | PASS (v2)
R-OSC-05 | OSCAL | All cross-references resolve (obs<->risk<->poam-item, subject<->inventory-item). | Constraint | Must | structural check | No dangling refs. | Test | PASS (v2)
DET: | Determinism | Reproducibility
R-DET-01 | Determinism | Same scan -> same OSCAL uuids (uuid5 over fixed namespace). | Non-functional | Must | poam._det | Re-run yields identical uuids. | Test | Built
R-DET-02 | Determinism | Output byte-stable for same input + timestamp. | Non-functional | Should | - | diff of two runs is empty. | Test | Open
EVID: | Evidence integrity | Privacy of evidence
R-EVID-01 | Evidence | Evidence carries hashes (command-sha256, stdout-sha256), never raw excerpts. | Constraint | Must | adapters/qureddy._evidence | No stdout/plaintext bodies in output. | Inspection | Built
R-EVID-02 | Evidence | No live scan-target data committed to repo artifacts. | Constraint | Must | session rule | example.com samples only in /tmp + examples, not product code. | Inspection | Held
CTRL: | Control mapping | finding -> control crosswalk
R-CTRL-01 | Control | finding->control crosswalk is authored, cited, human-reviewed; NOT LLM/scanner-guessed. | Constraint | Must | conformance lane; rev5 catalog | Every row cites a control statement; reviewer sign-off. | Inspection | OPEN
R-CTRL-02 | Control | Mapping is framework-scoped (SP 800-53 rev5) and ODP-aware. | Functional | Must | rev5 catalog ODPs | Row records ODP id + org-set value. | Inspection | OPEN
R-CTRL-03 | Control | POA&M states the verdict as an assertion tied to org ODP, not scanner truth. | Constraint | Must | v2 poam-item remarks | remarks makes the ODP dependency explicit. | Inspection | Met (v2)
R-CTRL-04 | Control | SC-13 primary, SC-12 supporting for KEX/crypto-protection findings; SC-8 excluded (overreach). | Functional | Should | SC-13/12/8 catalog text | SC-8 not emitted; SC-13+SC-12 present. | Inspection | Met (v2)
R-CTRL-05 | Control | No PQC/CNSA catalog exists; ODP bar is org-supplied, not shipped as fact. | Constraint | Must | reference tree has no PQC catalog | ODP value is caller/policy input. | Inspection | Held
VAL: | Validation | Checking output
R-VAL-01 | Validation | Structural validator (uuid validity, dangling refs) with no network/toolchain. | Functional | Must | validate.structural_errors | Returns [] for sound doc; lists problems otherwise. | Test | Built
R-VAL-02 | Validation | Optional oscal-cli integration when available (local or docker). | Functional | Should | validate.oscal_cli_available | Detects oscal-cli; runs full validation. | Demo | Partial
R-VAL-03 | Validation | CLI --validate flag runs the structural check. | Functional | Must | cli.main | --validate prints OK / errors + exit code. | Test | Built
CLI: | CLI | Command surface
R-CLI-01 | CLI | breachsafe-oscal poam --from <source> report.json. | Functional | Must | cli.py | Emits POA&M JSON to stdout. | Demo | Built
R-CLI-02 | CLI | Source registry is immutable at runtime (MappingProxyType). | Non-functional | Should | cli._ADAPTERS | Registry cannot be mutated. | Inspection | Built
R-CLI-03 | CLI | Explicit --from selection; no source auto-detection. | Constraint | Should | cli argparse choices | Unknown source rejected with choices. | Test | Built
PKG: | Packaging / NFR | Ship the library
R-PKG-01 | Packaging | Installable: pyproject.toml, __init__ files, README, LICENSE (Apache-2.0). | Non-functional | Must | package skeleton | pip install . succeeds; entry point runs. | Demo | OPEN
R-PKG-02 | Packaging | Python 3.11+ (matches type-hint syntax used). | Constraint | Should | from __future__ / X¦None | CI runs on 3.11+. | Test | OPEN
R-PKG-03 | Packaging | No runtime dependency on the NIST toolchain (validation is optional/external). | Constraint | Must | validate.py shutil.which | Library imports + emits with zero external tools. | Test | Built
R-PKG-04 | Packaging | Deterministic, side-effect-free core; I/O only at the CLI edge. | Non-functional | Should | emitters/adapters pure | Core functions do no I/O. | Inspection | Built
NG: | Non-goals | Explicitly out of scope
R-NG-01 | Non-goal | Does NOT assert an authoritative compliance pass/fail. | Constraint | Won't | CTRL-03 | Verdict is always ODP-conditioned. | Inspection | Held
R-NG-02 | Non-goal | Does NOT fabricate remediation milestones/dates. | Constraint | Won't | poam emitter | No invented deadlines. | Inspection | Held
R-NG-03 | Non-goal | Does NOT embed/transmit raw evidence excerpts. | Constraint | Won't | EVID-01 | Hashes only. | Inspection | Held

## Use-Cases
Use cases (N sources x M OSCAL shapes) + command + tier
UC | Command | Source | OSCAL target | Tier | Priority | Depends on | Status
UC-1 | poam generate | QuReddy scan JSON | POA&M | P0 | Must | T1 | Prototyped (v2 validated)
UC-2 | ar generate | QuReddy scan JSON | Assessment Results | P1 | Must | T1, T6 | Designed
UC-3 | component-definition generate | QuReddy CBOM | Component Definition | P2 | Should | - | Backlog
UC-4 | poam/ar generate | Prowler | POA&M / ar | P2 | Should | - | Backlog
UC-5 | ar generate | OCSF | Assessment Results | P3 | Could | - | Backlog
UC-6 | poam/ar generate --profile | Org PQC policy | Profile (CONSUME) | P1 | Should | T4 | Backlog
UC-7 | poam generate --merge | Existing POA&M + new scan | POA&M (merge) | P2 | Should | T2 | Backlog
UC-8 | poam/ar generate SRC... | Fleet scan (many endpoints) | POA&M / ar | P2 | Should | T3 | Backlog

## Parameters
Full parameter matrix - mint-oscal <model> generate
Flag | Applies to | OSCAL field / effect | Req | Default | Tier | Basis
COMMON: | all generate | shared by every <model> generate command
--from SOURCE | all | select the source adapter (qureddy; later prowler/ocsf) | yes | - | P0 | mint
SRC... / - | all | source report(s); MULTIPLE => fleet (many inventory-items) | yes | stdin | P0 | NIST
--to FORMAT | all | output encoding XML¦JSON¦YAML | no | JSON | P0 | NIST
DEST / -o FILE | all | destination | no | stdout | P0 | NIST
--overwrite | all | overwrite DEST if exists | no | off | P0 | NIST
--title TEXT | all | metadata/title | no | derived | P0 | OSCAL
--doc-version VER | all | metadata/version | no | 0.1.0 | P0 | OSCAL
--oscal-version VER | all | metadata/oscal-version | no | 1.1.2 (+1.2.2 target prop) | P0 | OSCAL
--now TS | all | metadata/last-modified (DETERMINISM pin) | no | scan completed_at | P0 | mint
--published TS | all | metadata/published | no | omitted | P1 | OSCAL
--prepared-by NAME | all | role + party(org) + responsible-party | no | omitted | P0 | OSCAL
--namespace UUID | all | uuid5 seed for reproducible ids | no | fixed BreachSAFE ns | P1 | mint
--validate | all | oscal-cli if present, else structural; exit 1 on fail | no | off | P0 | mint
-q/--quiet, --no-color, --show-stack-trace, --version, -h | all | NIST global flags (verbatim) | no | - | P0 | NIST
POAM: | poam | Plan of Action & Milestones (UC-1)
--system-id VALUE | poam | system-id (XOR import-ssp) | one-of | subject locator | P0 | OSCAL
--system-id-type URI | poam | system-id/@identifier-type | no | https://ietf.org/rfc/rfc3986 | P0 | OSCAL
--import-ssp HREF | poam | import-ssp (XOR system-id) | one-of | - | P1 | OSCAL
--cbom HREF | poam | observation/relevant-evidence (CycloneDX CBOM) | no | omitted | P0 | OSCAL
--merge PRIOR | poam | reconcile item status by uuid vs a prior POA&M (T2/UC-7) | no | - | P2 | mint
AR: | ar | Assessment Results (UC-2) - GROUNDED required fields
--import-ap HREF | ar | import-ap - REQUIRED by the AR model (references an Assessment Plan) | YES | - | P1 | OSCAL (grounded)
--result-title TEXT | ar | results/title | no | '<source> scan results' | P1 | OSCAL
--start TS | ar | results/start (required) | no | scan started_at | P1 | OSCAL
--end TS | ar | results/end | no | scan completed_at | P1 | OSCAL
COMPONENT-DEFINITION: | component-definition | crypto inventory (UC-3)
--component-type TYPE | component-definition | component/@type (software/service/...) | no | derived from CBOM asset | P2 | OSCAL
PROFILE (emit, optional): | profile | emit a PQC overlay (inverse of UC-6)
--import HREF | profile | import - REQUIRED (the catalog being tailored) | YES | - | P3 | OSCAL (grounded)
--set-param ID=VALUE | profile | modify/set-parameter (e.g. sc-13_odp.02=PQC) | no | - | P3 | OSCAL
--include-control ID | profile | import/include-controls | no | all | P3 | OSCAL
CONSUME (shared): | poam, ar | read an external OSCAL artifact to source the verdict
--profile PATH | poam, ar | CONSUME a Profile to source ODP values instead of a literal (T4/UC-6) | no | omitted | P1 | OSCAL
--framework ID | poam, ar | which crosswalk control set applies | no | sp800-53r5 | P1 | mint
SOURCE-SPECIFIC: | adapter | flags a given --from adapter may add
--prowler-format FMT | --from prowler | ocsf ¦ native | no | ocsf | P2 | mint

## OSCAL-Shapes
OSCAL shapes - one requirement set per model (roots grounded)
Root fields now GROUNDED from reference/OSCAL metaschemas. Deeper per-result / per-observation subfields still marked CONFIRM - read before writing that emitter.
Shape | mint role | Required roots (grounded from metaschema) | Deeper fields | Tier | Verified
POA&M | EMIT | uuid; metadata; (system-id XOR import-ssp); >=1 poam-item | poam-item{title,description} | P0 | YES - validated
Assessment Results (ar) | EMIT | uuid; metadata; import-ap (REQUIRED); >=1 result | result{title,description,start}; observations/findings/risks | P1 | roots grounded; subfields CONFIRM
Component Definition | EMIT | uuid; metadata; >=1 component OR capability | component{type,title,description} | P2 | roots grounded; subfields CONFIRM
Profile | CONSUME / EMIT | uuid; metadata; >=1 import | import{href}; modify/set-parameters | P1/P3 | roots grounded; subfields CONFIRM
Catalog | CONSUME | controls, params, groups | - | P1 | YES - read
SSP | LINK | referenced via POA&M import-ssp; not emitted | - | P2 | n/a
Assessment Plan | SKIP / stub? | forward-looking; but AR requires import-ap (see T6) | - | - | see T6

## CLI-Design
CLI design requirements (NIST-aligned, composable)
ID | Requirement | Rationale / prior art | Priority | Status
R-CLI-D01 | Grammar mirrors oscal-cli: mint-oscal <model> generate [opts] <src> [dest]. | Prefer NIST taxonomy; users already know oscal-cli's model+operation shape. | Must | Decided
R-CLI-D02 | Models use NIST names exactly: poam, ar, component-definition (emit); profile, catalog (consume). | ar (not 'sar'); component-definition (not 'component') per oscal-cli. | Must | Decided
R-CLI-D03 | Production verb = generate; validate & convert DELEGATE to oscal-cli, not reimplemented. | NIST owns validate/convert; mint owns production. | Must | Decided
R-CLI-D04 | Source adapter via --from <source> (required, explicit; no auto-detection). | mint ingests non-OSCAL; NIST has no analog, so this is a deliberate divergence. | Must | Built
R-CLI-D05 | Composable filter: <src>/'-'/stdin in, dest/-o/stdout out. | Chains: mint-oscal poam generate --from qureddy scan.json ¦ oscal-cli poam validate - | Must | Designed
R-CLI-D06 | Output encoding via --to XML¦JSON¦YAML (default JSON). | Adopt NIST convert's --to verbatim. | Should | Designed
R-CLI-D07 | --overwrite guards an existing destination. | NIST convention. | Should | Designed
R-CLI-D08 | Adopt NIST global flags verbatim: -q/--quiet, --no-color, --show-stack-trace, --version, -h. | Muscle-memory parity with oscal-cli. | Should | Designed
R-CLI-D09 | --now TS pins metadata/last-modified; default = scan completion time, NOT wall-clock. | Determinism: wall-clock timestamps break byte-stable diffs in CI. | Must | Designed
R-CLI-D10 | Production-context flags: --system-id, --import-ssp, --profile, --prepared-by (never fabricated). | Program inputs mint needs to BUILD a doc; NIST only transforms existing ones. | Should | Designed
R-CLI-D11 | --validate shells to oscal-cli if present, else internal structural check. | Reuse the NIST validator. | Should | Partial
R-CLI-D12 | Introspection commands: mint-oscal sources, mint-oscal shapes. | Discoverability of adapters/targets. | Should | Open
R-CLI-D13 | Exit codes: 0 ok; 1 validation/structural fail; 2 usage error. | Scriptable / CI-friendly. | Must | Open
R-CLI-D14 | Library API mirrors the CLI 1:1: convert(document, *, source, shape, ...) facade. | QuReddy/managed-engine call the lib; TAO/Osmedeus call the CLI; same params. | Should | Partial
R-CLI-D15 | NOT a Trestle-style stateful repo tool; no in-place editing of a working dir. | Trestle owns that lane; mint is a producing filter. | Must | Decided

## CLI-Reference
CLI reference - mint-oscal <model> generate --from <source> [SRC] [DEST]
Element | Kind | Definition | Default | Origin
MODELS: |  | the OSCAL shape to mint
poam | model (emit) | Plan of Action & Milestones - open findings + remediation plan/owners/milestones | - | NIST
ar | model (emit) | Assessment Results - the faithful record: observations, findings, risks | - | NIST
component-definition | model (emit) | Components and how they implement/relate to controls (crypto inventory) | - | NIST
profile | model (consume) | Tailored control baseline + set-parameters (the ODP / compliance bar) | - | NIST
catalog | model (consume) | Control source text, e.g. SP 800-53 rev5 | - | NIST
OPERATION: |  | what mint does to produce it
generate | operation | Build the named model from a foreign source report via the IR | - | mint
validate | operation (deferred) | OSCAL conformance check - delegates to oscal-cli | - | oscal-cli
convert | operation (deferred) | Re-encode OSCAL XML/JSON/YAML - delegates to oscal-cli | - | oscal-cli
FLAGS:
--from SOURCE | flag (required) | Which adapter parses the input (qureddy; later prowler, ocsf) | required | mint
SRC / - | positional | Source report file/URL, or '-'/omitted = stdin | stdin | NIST
DEST / -o FILE | positional/flag | Where to write the OSCAL; omitted = stdout | stdout | NIST
--to FORMAT | flag | Output encoding: XML ¦ JSON ¦ YAML | JSON | NIST
--overwrite | flag | Overwrite DEST if it already exists | off | NIST
--now TS | flag | Pin metadata/last-modified for deterministic output | scan completion time | mint
--system-id ID | flag | System identifier for the subject | subject locator | mint
--import-ssp HREF | flag | Link an existing SSP instead of a standalone system-id | none | mint
--profile PATH | flag | Consume an OSCAL Profile to source the ODP/compliance bar | none | mint
--prepared-by NAME | flag | Responsible-party provenance in metadata | none | mint
--validate | flag | Run oscal-cli if present, else internal structural check | off | mint
-q, --quiet | flag | Errors only | off | NIST
--no-color | flag | No ANSI color | off | NIST
--show-stack-trace | flag | Full stack trace on error | off | NIST
--version / -h, --help | flag | Tool + supported OSCAL version / help | - | NIST
INTROSPECTION: |  | no model
mint-oscal sources | command | List available source adapters | - | mint
mint-oscal shapes | command | List emittable OSCAL models | - | mint
EXIT CODES:
0 | exit | Success | - | -
1 | exit | Validation / structural failure | - | -
2 | exit | Usage error (bad flags, unknown source/model) | - | -

## NIST-Parity
Parameter parity vs NIST oscal-cli
NIST oscal-cli | mint-oscal | Status | Note
-h/--version/-q/--quiet/--no-color/--show-stack-trace | same | ADOPT | global flags verbatim
shell-completion (bash/zsh) | same | ADOPT | match NIST
model groups poam/ar/component-definition/profile/catalog | same subset | ADOPT | model-first taxonomy
--to XML¦JSON¦YAML | --to | ADOPT | output encoding
--overwrite | --overwrite | ADOPT
<source> [dest] positional | same | ADOPT | stdin/stdout default
--as FORMAT (input encoding) | - | N/A | mint input is foreign/IR, not OSCAL
validate: -c/-o SARIF/--sarif-*/--disable-*/--path-format/--threads | --validate | DELEGATE | mint shells to oscal-cli; no re-implementation
resolve-profile | --profile (consume) | PARTIAL | full resolution later
metaschema | - | N/A | NIST-internal
(none) | --from --now --system-id[-type] --import-ssp --import-ap --cbom --profile --framework --prepared-by --namespace --merge --result-title --start --end --title --doc-version --oscal-version | SUPERSET | production flags NIST has no analog for

## Coding-Standards
Coding-standard parity (>= NIST OSCAL tools)
Dimension | oscal-cli (Java) | Trestle (Python) | mint-oscal target
Format | Java fmt | ruff format (hatch) | ruff format
Lint | PMD | ruff E,W,I,B,C4,T20,SIM,S | SUPERSET: +F,UP,PTH,RUF,ANN,D
Static analysis | SpotBugs | - | mypy --strict
Type check | typed | mypy | mypy --strict
Security lint | SpotBugs | ruff S (bandit) | ruff S
No stray print | - | T20 | T20
License headers | license-maven-plugin | headers | SPDX enforced (on every .py)
Tests | JUnit | pytest+xdist+randomly | pytest+randomly (TESTER-owned)
Coverage gate | jacoco | coverage~=7.4 | coverage gate
Pre-commit | - | yaml/merge/no-commit-to-branch/fmt/mdformat | same + ruff hooks
CI | GH Actions | GH Actions + Sonar | GH Actions: ruff+mypy+pytest
Docstrings | Javadoc | - | ruff D (pydocstyle)
Verdict | - | - | >= NIST; meets+exceeds Trestle's Python gate

## Tool-Comparison
Tool comparison - where mint-oscal fits the OSCAL ecosystem
Capability | mint-oscal | oscal-cli (NIST) | Trestle (IBM) | oscalkit | RegScale
Produce OSCAL FROM scanner findings | YES (core) | no (transforms OSCAL only) | ~ authoring | no | yes (commercial)
PQC / crypto-aware findings -> OSCAL | YES (unique) | no | no | no | no
Validate / convert OSCAL | delegates to oscal-cli | yes | yes | yes | yes
Composable stdin->stdout filter | yes | yes | ~ repo tool | yes | ~
Deterministic git-diffable output | yes | n/a | yes (splits files) | n/a | ?
Emit model coverage | poam, ar, component-definition | all (transform) | authoring set | convert | all
Language | Python | Java | Python | Go | SaaS
License | Apache-2.0 | public domain | Apache-2.0 | Apache-2.0 | commercial

## Open-Decisions
Open architectural decisions (ADR ledger)
ID | Decision | Options | Recommendation / choice | Status | Affects
ADR-0001 / T1 | Primary OSCAL target for scan findings | A) POA&M only B) ar canonical + POA&M derived C) both independent | B - ar is the faithful 'what we observed'; POA&M is the open-risk extract (flagship). | Proposed | emitters; UC-1, UC-2
ADR-0002 / CLI-1 | CLI shape | model-first (mint <model> generate) ¦ verb (convert --to) ¦ trestle-tasks | model-first + composable filter, NIST-aligned. | Proposed | CLI
ADR-0003 / NAME | Package naming | repo breachsafe-mint-oscal ¦ pypi mint-oscal ¦ import mint_oscal | As stated; brand-consistent with mint-sts. | Accepted | packaging
ADR-0004 / T8 | Adapter placement (ports & adapters) | A) adapters in core B) fully agnostic (caller passes IR) C) agnostic core + optional edge plugins | C - agnostic core; IR promoted to published contract mint.ir.v1; sources emit IR or ship an adapter plugin; qureddy bundled as optional convenience. | Accepted | whole src layout; IR contract; CLI --from
ADR-0005 / T7 | Render strategy for XML/YAML | A) reimplement OSCAL XML B) JSON native + shell XML/YAML to oscal-cli | B - JSON native (no dep); XML/YAML optional via oscal-cli (runtime dep only when used). | Accepted | render.py; R-PKG-03
T2 | Re-scan lifecycle / state | A) stateless snapshot B) merge & reconcile by uuid (--merge) | A for v1; B for v2. | Open | UC-7
T3 | Single-subject vs fleet | A) one inventory-item B) many (SRC..., findings->subject) | B - IR carries Finding.subject. | Open | UC-8
T4 | Source of the compliance bar (ODP) | A) hardcoded string B) consume an OSCAL Profile (--profile) | B - ties verdict to a cited artifact. | Open | UC-6
T5 | SSP linkage | A) standalone system-id B) optional import-ssp | B - support both; standalone default. | Open | UC-1
T6 | AR requires import-ap (a raw scan has no Assessment Plan) | A) require --import-ap B) auto-generate a minimal AP stub C) placeholder AP | A for v1; B later. | Open | UC-2; ar generate

## Grounding
Primary-source grounding (proof, not guesses)
ID | Primary source | Location | What it establishes | Requirements
G-01 | OSCAL POA&M metaschema | reference/OSCAL/src/metaschema/oscal_poam_metaschema.xml | Required POA&M fields, element order, schema-version 1.2.2. | R-OSC-02, R-OSC-04
G-02 | SP 800-53 rev5 catalog | reference/oscal-content/.../NIST_SP-800-53_rev5_catalog.json | SC-13 / SC-12 / SC-8 verbatim text + organization-defined parameters (ODPs). | R-CTRL-01..05
G-03 | Real POA&M example (ifa) | reference/oscal-content/examples/poam/xml/ifa_plan-of-action-and-milestones.xml | Concrete, valid POA&M structure to model against. | R-OUT-01
G-04 | NIST-lineage oscal-cli 3.2.0 | docker ghcr.io/metaschema-framework/oscal-cli:latest | Validates our POA&M clean; supports both 1.1.2 and 1.2.2 (corrects stale 1.0.3=1.1.2-only note). | R-OSC-03, R-OSC-01
G-05 | Compliance Trestle poam.py | reference/compliance-trestle/trestle/oscal/poam.py | OSCAL 1.2.1 object model; version regex ^1.2.[0-1]$ (why we declare 1.1.2 for interop). | R-OSC-01
G-06 | CycloneDX CBOM (QuReddy) | qureddy output/cbom*.py | Companion crypto evidence artifact linked via relevant-evidence. | R-OUT-04
G-07 | Validated prototype v2 | /tmp/oscal/example.poam.v2.xml (examples/) | End-to-end proof: live scan -> standalone, readable, valid POA&M. | R-OUT-02..05, R-OSC-*

## Control-Crosswalk
finding -> control crosswalk
DRAFT - starting point only. NOT an authored compliance decision. Requires human conformance review + citation sign-off (R-CTRL-01). SC-8 intentionally excluded as overreach.
Finding (readiness) | Primary control | Supporting | ODP id | ODP value (ORG-SET) | Verdict basis | Catalog citation | Reviewer | Status
quantum_vulnerable (classical KEX) | SC-13 | SC-12 | sc-13_odp.02 | CNSA 2.0 / PQC required | Deficiency IF org ODP requires PQC; otherwise informational. | SC-13(b): implement {sc-13_odp.02 types of cryptography} | UNREVIEWED | DRAFT
classical certificate signature | SC-13 | SC-12 | sc-13_odp.02 | CNSA 2.0 / PQC required | Same ODP dependency; signature agility. | SC-13(b) | UNREVIEWED | DRAFT
quantum_ready / hybrid | SC-13 | SC-12 | sc-13_odp.02 | CNSA 2.0 / PQC required | Likely compliant; record as satisfied observation. | SC-13(b) | UNREVIEWED | DRAFT

## Legend
Legend
Field | Value | Meaning
Priority:
Priority | Must | Release blocked without it.
Priority | Should | Important; ship without only with a reason.
Priority | Could | Desirable; roadmap.
Priority | Won't | Explicit non-goal / out of scope now.
Type:
Type | Functional | What the system does.
Type | Non-functional | Quality attribute (perf, determinism, packaging).
Type | Constraint | A boundary that must hold.
Verify:
Verify | Test | Automated check (tester-owned).
Verify | Demo | Run it and observe (e.g. oscal-cli validate).
Verify | Inspection | Read the code/doc.
Verify | Analysis | Reason from spec/model.
Status:
Status | Built / Met / PASS | Implemented and/or evidenced.
Status | Designed / Partial | Decided or partially done.
Status | Open / OPEN / Backlog / Deferred | Not started / later.
Status | Held | A constraint currently being honored.